## Task 3 Risk Assessment and Moni
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Risk ID | Risk Category | Risk Description | Inherent Likelihood | Inherent Impact | Inherent Risk Rating | Existing Controls | Control Effectiveness (Design/Op) | Residual Likelihood | Residual Impact | Residual Risk Rating | Mitigation Action Plan | Owner | Due Date | Status
CR-001 | AML/CTF | Inadequate CDD/KYC for new merchant onboarding | High | Catastrophic | Critical | Manual review of basic documents; no automated screening; limited beneficial ownership collection. | Ineffective | High | Catastrophic | Critical | Implement automated KYC/IDV solution; revise CDD policy; mandatory training for onboarding team. | Head of AML | 90 Days | In Progress
CR-002 | PCI DSS | Data Breach due to unpatched legacy systems | High | Catastrophic | Critical | Some patching occurs; no centralized vulnerability management; limited real-time monitoring. | Weak | High | Severe | High | Implement patch management program; deploy SIEM; conduct penetration tests; upgrade critical systems. | Head of IT Sec | 90 Days | In Progress
CR-003 | Third-Party | Vendor non-compliance with data security standards | Medium | Severe | High | Basic vendor contract; no dedicated due diligence process for compliance; limited ongoing monitoring. | Very Weak | Medium | Severe | High | Develop Third-Party Risk Management Policy; conduct vendor security assessments; add compliance clauses to contracts. | CCO | 120 Days | Not Started
CR-004 | Governance | Absence of formal compliance officer | High | Catastrophic | Critical | Scattered responsibilities; informal reporting. | Non-Existent | High | Catastrophic | Critical | Appoint CCO; establish Compliance Department; define roles/responsibilities. | Board / CEO | 30 Days | Completed
CR-005 | AML/CTF | Insufficient transaction monitoring for fraud/ML | High | Severe | High | Rule-based system only; high false positives; no behavioral analytics; manual review backlog. | Ineffective | High | Severe | High | Implement advanced transaction monitoring system (AI/ML); hire additional AML analysts; optimize rules. | Head of AML | 180 Days | Planning