## Task 5 Implementation Roadmap (
Activity | Key Deliverable | Dependencies | Responsible Teams | Start Date (Approx.) | End Date (Approx.)
Day 1-14: Emergency Risk Assessment & Gap Analysis | Updated Risk Register & Gap Report (AML, PCI) | - | Compliance, Risk, IT Security | Day 1 | Day 14
Day 1-30: Policy Review & Update (Key) | Core AML & PCI DSS Policies/Procedures V1.0 | Risk Assessment Results | Compliance, Legal, IT Security | Day 1 | Day 30
Day 1-45: Centralized Document Repository Setup | Basic DMS Operational (for critical documents) | IT Infrastructure | IT, Compliance | Day 1 | Day 45
Day 15-60: Enhanced AML Transaction Monitoring Rules | Optimized Rules & Alert Review Process | Current System Capabilities, Data Access | AML Compliance, IT | Day 15 | Day 60
Day 30-75: Essential Employee Training Rollout | Acknowledged & Completed Core Training | Updated Policies | HR, Compliance | Day 30 | Day 75
Day 45-80: PCI DSS Vulnerability Management Sprint | Reduced Critical/High Vulnerabilities | IT Security Team Availability, Tools | IT Security | Day 45 | Day 80
Day 60-90: Initial Compliance Reporting Setup | Basic Dashboard & Mgmt Report Template | Data Feeds, DMS | Compliance, IT, BI | Day 60 | Day 90
Day 75-90: Regulatory Communication & Progress Report | Formal Communication to Regulators | All preceding activities, report data | Legal, CCO | Day 75 | Day 90